## Tasks and Timeline
Sauce & Spoon Project Plan
| Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS | [7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone: Initiation
1.1 | Install tablets in the bar areas at the Downtown and North restaurant locations |  |  |  | 5
1.2 | Plan meeting with staff to kickoff project |  |  |  | 2
2 | Milestone: Sourcing
2.1 | Generate quotes and review costs |  |  |  | 3.5
2.2 | Researching tablet features |  |  |  | 3
2.3 | Comparing tablet prices |  |  |  | 2
2.4 | Create contracts and statements of work for vendors |  |  |  | 5
2.5 | Shipping and receiving tablets |  |  |  | 9.5
2.6 | Create a launch day plan: staffing, troubleshooting, etc. |  |  |  | 5
2.7 | Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  |  |  | 2
2.8 | Schedule an electrician |  |  |  | 1.5
3 | Milestone: Install tablets
3.1 | Enable GPS location services on each tablet |  |  |  | 2
3.2 | Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  |  |  | 4
3.3 | Create messaging about payment portal security to display on the tablets |  |  |  | 3
3.4 | Include payment security talking points in waitstaff training |  |  |  | 2
4 | Milestone: Training
4.1 | Revamp menu |  |  |  | 5
4.2 | Schedule training |  |  |  | 8
4.3 | Pre-training meeting to introduce tablets and changes to staff |  |  |  | 1
4.4 | Train the staff to update the menu |  |  |  | 2
4.5 | Train management, FOH staff, and BOH staff |  |  |  | 2
5 | Milestone: Launch
5.1 | Invite friends and family to do a test run of the tablets. |  |  |  | 4
5.2 | Conduct test run |  |  |  | 9.5
5.3 | Implement a post-dining survey to assess customer satisfaction |  |  |  | 3

## Task Brainstorm
Task Brainstorm
| Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
WBS
1 | Milestone: Initiation
1.1 | Install tablets in the bar areas at the Downtown and North restaurant locations |  | 5 | 3 | 5 | 7 | H
1.2 | Plan meeting with staff to kickoff project |  | 2 | 1 | 2 | 3 | H
2 | Milestone: Sourcing
2.1 | Generate quotes and review costs |  | 3.5 | 2 | 3 | 7 | H
2.2 | Researching tablet features |  | 3 | 1 | 3 | 5 | M
2.3 | Comparing tablet prices |  | 2 | 1 | 2 | 3 | H
2.4 | Create contracts and statements of work for vendors |  | 5 | 2 | 5 | 8 | M
2.5 | Shipping and receiving tablets | delay in shipping causing this long duration | 9.5 | 7 | 9 | 14 | M
2.6 | Create a launch day plan: staffing, troubleshooting, etc. |  | 5 | 3 | 4 | 11 | H
2.7 | Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  | 2 | 1 | 2 | 3 | M
2.8 | Schedule an electrician |  | 1.5 | 1 | 1.5 | 2 | H
3 | Milestone: Install tablets
3.1 | Enable GPS location services on each tablet |  | 2 | 1 | 2 | 3 | M
3.2 | Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  | 4 | 2 | 4 | 6 | H
3.3 | Create messaging about payment portal security to display on the tablets |  | 3 | 1 | 3 | 5 | M
3.4 | Include payment security talking points in waitstaff training |  | 2 | 1 | 2 | 3 | M
4 | Milestone: Training
4.1 | Revamp menu |  | 5 | 3 | 5 | 7 | H
4.2 | Schedule training |  | 8 | 4 | 8 | 12 | M
4.3 | Pre-training meeting to introduce tablets and changes to staff |  | 1 | 0.5 | 1 | 1.5 | H
4.4 | Train the staff to update the menu |  | 2 | 1 | 2 | 3 | M
4.5 | Train management, FOH staff, and BOH staff |  | 2 | 1 | 2 | 3 | M
5 | Milestone: Launch
5.1 | Invite friends and family to do a test run of the tablets. |  | 4 | 2 | 3 | 10 | H
5.2 | Conduct test run |  | 9.5 | 5 | 10 | 12 | M
5.3 | Implement a post-dining survey to assess customer satisfaction |  | 3 | 2 | 3 | 4 | M

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Retention - Improved | Have we improved customer satisfaction? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | Are you satisfied with your service? | FALSE
Customer Retention - Improved | Are customers receiving the correct orders? | Guests who use the tablets receive correct orders 95% of time | Are you receiving everything you want in your order? | FALSE
Tablet Functionality and Ease of Use - Overall | Are customers having a better dining experience with the tablets? | Guests have shorter wait times and more food options on menu | What are some things that you liked about using tablets for ordering? | FALSE
Lobby - less than 10 Minutes | How quickly are customers learning how to navigate the tablets? | Guests can order off menu 20% faster since they don't have to wait for server to order | Did you experience any difficulty in ordering on the tablets? | FALSE
Tablet Functionality and Ease of Use - Overall | Do all the tablets work as expected? | Tablet error logs report a maximum of one error per shift | Did tablets work as you expected? | FALSE
Customer Retention - Improved | True or false on good customer experience? | Customers take 10% less time to order due to good design. | Is it true our restaurant has improved the customer experience with tablets? | FALSE
Tablet Functionality and Ease of Use - Overall | On a scale of 1–5, where 1 is “very easy” and 5 is “not at all easy,” how easy is this feature to use? | Ordering food button on tablet menu | On a scale of 1–5, where 1 is “very easy” and 5 is “not easy at all ,” how easy is this feature to use? | FALSE
Product mix - Improved | What type of food items did you search for first on tablet? | Finding appetizers and drinks take 10% less time | What type of food items did you search for first on tablet? | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Customer Retention - Improved | Have we improved customer satisfaction? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | Are you satisfied with your service? | Yes/No | Yes | No
Customer Retention - Improved | Are customers receiving the correct orders? | Guests who use the tablets receive correct orders 95% of time | Are you receiving everything you want in your order? | Yes/No | Yes | No
Tablet Functionality and Ease of Use - Overall | Are customers having a better dining experience with the tablets? | Guests have shorter wait times and more food options on menu | What are some things that you liked about using tablets for ordering? | Open-ended
Lobby - less than 10 Minutes | How quickly are customers learning how to navigate the tablets? | Guests can order off menu 20% faster since they don't have to wait for server to order | Did you experience any difficulty in ordering on the tablets? | Open-ended
Tablet Functionality and Ease of Use - Overall | Do all the tablets work as expected? | Tablet error logs report a maximum of one error per shift | Did tablets work as you expected? | Yes/No | Yes | No
Customer Retention - Improved | True or false on good customer experience? | Customers take 10% less time to order due to good design. | Is it true our restaurant has improved the customer experience with tablets? | True/False
Tablet Functionality and Ease of Use - Overall | On a scale of 1–5, where 1 is “very easy” and 5 is “not at all easy,” how easy is this feature to use? | Ordering food button on tablet menu | On a scale of 1–5, where 1 is “very easy” and 5 is “not at all easy,” how easy is this feature to use? | Scaled
Product mix - Improved | What type of food items did you search for first on tablet? | Finding appetizers and drinks take 10% less time | What type of food items did you search for first on tablet? | Multiple choice | Appetizers | Drinks | Meals | Desserts